## Product Catalog
Project Name | Learner's Academy
StakeHolders/Customers/Users | ABC etc.
Created By | Siddhant Nalawade
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Criteria
Design and develop a backend administrative portal for an online management system in school. (Learner'sAcademy_Epic_001) | US001 | Set up a master list of all the subjects for all the classes. | To set up a master list of all subjects for all the classes for its operations. | New
| US002 | Set up a master list of all the teachers. | To set up a master list of all the teachers to assign them classes and subjects. | New
| US003 | Set up a master list of all the classes | To set up a master list of all the classes to assign them teachers and subjects. | New
| US004 | Assign classes for subjects from the master list. | To assign the classes their subjects from the master list. | New
| US005 | Assign teachers to a class for a subject. | To assign the teachers a class for a subject. | New
| US006 | Assign teachers to a class for a subject. | To set up a master list of all the students for all the classes. | New

## Sprint Planning
Project Name | LockedMe.com
Scrum Team | Dev, QA, PO, Scrum Master etc.
Created By | Siddhant Nalawade
Epic | User Story ID | Feature/Title | User Story | Story Points | Sprint
Design and develop a backend administrative portal for an online management system in school. (Learner'sAcademy_Epic_001) | US001 | Set up a master list of all the subjects for all the classes | To set up a master list of all subjects for all the classes for its operations. | 8 | 1
| US002 | Set up a master list of all the teachers | To set up a master list of all the teachers to assign them classes and subjects. | 3 | 1
| US003 | Set up a master list of all the classes | To set up a master list of all the classes to assign them teachers and subjects. | 5 | 2
| US004 | Assign classes for subjects from the master list | To assign the classes their subjects from the master list. | 5 | 2
| US005 | Assign teachers to a class for a subject | To assign the teachers a class for a subject. | 4 | 3
| US006 | Get a master list of students | To set up a master list of all the students for all the classes. | 8 | 3